## Deliverable 1 Sprint
Deliverable 1
ID | Story Title | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Priority | Story Status | Story Points | Story Points Completed | Names and Contribution Percentage
Core User Stories
C1 | Feedback with Emotional Context | As a user of this system (student, professor, administrator, etc.) when I encounter a problem, I want to communicate not only the technical details but also how it makes me feel, so that the impact of the problem is fully understood. | C1 - Story Document | Not Assigned |  | Unassigned | Medium | Waiting | 8 | 0
C2 | Feedback History & Tracking | As a feedback provider, I want to track the status of my feedback, so I can understand where it's at in the review process and what actions are being taken. | C2 - Story Document | Not Assigned |  | Unassigned | Medium | Waiting | 8 | 0
C3 | Community Connection on Shared Issues | As a student, I want to connect with others who've shared similar feedback or faced similar issues, so we can collaborate on solutions or offer mutual support. | C3 - Story Document | Not Assigned |  | Unassigned | High | Waiting | 10 | 0
C4 | Direct Communication with Decision Makers | As a student, if I have a pressing issue, I want an option to message a specific authority, like a professor or department head, to directly address my concern. | C4 - Story Document | Not Assigned |  | Unassigned | Low | Waiting | 5 | 0
C5 | Anonymity | As a user (student, professor, administrator, etc.), I want to ask for help anonymously, so that I can alleviate my anxieties and ensure I succeed in the class. | C5 - Story Document | Not Assigned |  | Unassigned | High | Waiting | 8 | 0
C6 | Freedom to Ask Any Questions | As a student, I want to ensure that I can submit personal questions anonymously or questions that might not be “good” questions to get help without being judged by other classmates. |  | Not Assigned |  | Unassigned | High | Waiting | 8 | 0
C7 | Consistent Assistance | As a student, I want an active platform to consistently get assistance, so I can understand the material without repeatedly exposing my struggles. |  | Not Assigned |  | Unassigned | High | Waiting | 10 | 0
C8 | More Reliable than a Help Lab | As a student, I want an app to seek assistance, so that I can get help without the embarrassment I feel in a help lab. |  | Not Assigned |  | Unassigned | High | Waiting | 10 | 0
C9 | Instant Messaging to Professors | As a student, I want an app to instantly message my professors during lectures, so I can clarify doubts without drawing attention. |  | Not Assigned |  | Unassigned | Low | Waiting | 4 | 0
C10 | Convenient Messaging | As a student, I want an app with a class-wide forum, so I can seek help outside of help center hours and leverage peer insights. |  | Not Assigned |  | Unassigned | Low | Waiting | 5 | 0
Social and Collaborative Stories
S1 | Connections with Similar Students | As a computer science student, I want to be able to easily find and connect with other students who are in the same course so that we can form study groups, share our learning resources, and support each other in the learning process. |  | Not Assigned |  | Unassigned | Medium | Waiting | 7 | 0
S2 | A Platform to Make Friends/Connections within your Major | As a computer science student, I want a platform to interact with my peers, so that I can build connections and not feel alienated. |  | Not Assigned |  | Unassigned | Low | Waiting | 8 | 0
S3 | Working Together with Peers | As a student, I want a platform to discuss assignments with my peers, so that I can gain diverse insights, especially when I can't attend office hours. |  | Not Assigned |  | Unassigned | Low | Waiting | 6 | 0
Mentorship and Learning Stories
M1 | Receiving Help from Course Alumni | As a student who is navigating the challenging coursework, I want an application where I can reach out to students who have completed this class or people like alumni who have gone through similar challenges, so I can gain insights from their experiences, and feel more confined in my academic journey. |  | Not Assigned |  | Unassigned | High | Waiting | 8 | 0
M2 | Choice Collaborations | As a computer science senior, I want to choose who I collaborate with, so that I can offer help based on my experiences without external pressures. |  | Not Assigned |  | Unassigned | Low | Waiting | 5 | 0
Platform and User Experience Stories
P1 | Comparative Insights from Past Solutions | As a student, I want to use a platform tailored to academic needs, ensuring that it stands out from general-purpose platforms like Discord or Social Media, so I can more effectively engage and collaborate in my academic journey. |  | Not Assigned |  | Unassigned | Medium | Waiting | 7 | 0
P2 | Around the Clock Help | As a student, I want a platform to anonymously seek immediate help, so I can get responses even outside typical hours and not fall behind on assignments. |  | Not Assigned |  | Unassigned | High | Waiting | 9 | 0
P3 | Autocorrect Amenities | As a bilingual student, I want to have predictable and autocorrect features so that when I misspell or can’t remember something it will still make sense. |  | Not Assigned |  | Unassigned | Low | Waiting | 6 | 0

## Deliverable 2 Sprint
Deliverable 2
ID | Story Title | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Priority | Story Status | Story Points | Story Points Completed | Names and Contribution Percentage
Core User Stories
C1 | Feedback with Emotional Context | As a user of this system (student, professor, administrator, etc.) when I encounter a problem, I want to communicate not only the technical details but also how it makes me feel, so that the impact of the problem is fully understood. | C1 - Story Document | Not Assigned |  | Unassigned | Medium | Waiting | 8 | 0 | A.B: 40%, C.D: 60%
C2 | Feedback History & Tracking | As a feedback provider, I want to track the status of my feedback, so I can understand where it's at in the review process and what actions are being taken. | C2 - Story Document | Not Assigned |  | Unassigned | Medium | Waiting | 8 | 0 | A.B: 20%, E.F: 30%, G.H: 25%, I.J: 25%
C3 | Community Connection on Shared Issues | As a student, I want to connect with others who've shared similar feedback or faced similar issues, so we can collaborate on solutions or offer mutual support. | C3 - Story Document | Not Assigned |  | Unassigned | High | Waiting | 10 | 0 | E.F: 50%, I.J: 50%
C4 | Direct Communication with Decision Makers | As a student, if I have a pressing issue, I want an option to message a specific authority, like a professor or department head, to directly address my concern. | C4 - Story Document | Not Assigned |  | Unassigned | Low | Waiting | 5 | 0 | C.D: 50%, K.L: 50%
C5 | Anonymity | As a user (student, professor, administrator, etc.), I want to ask for help anonymously, so that I can alleviate my anxieties and ensure I succeed in the class. | C5 - Story Document | Not Assigned |  | Unassigned | High | Waiting | 8 | 0 | A.B: 15%, C.D: 25%, E.F: 25%, G.H: 35%
C6 | Freedom to Ask Any Questions | As a student, I want to ensure that I can submit personal questions anonymously or questions that might not be “good” questions to get help without being judged by other classmates. |  | Not Assigned |  | Unassigned | High | Waiting | 8 | 0 | G.H: 40%, I.J: 60%
C7 | Consistent Assistance | As a student, I want an active platform to consistently get assistance, so I can understand the material without repeatedly exposing my struggles. |  | Not Assigned |  | Unassigned | High | Waiting | 10 | 0 | A.B: 20%, E.F: 30%, G.H: 25%, I.J: 25%
C8 | More Reliable than a Help Lab | As a student, I want an app to seek assistance, so that I can get help without the embarrassment I feel in a help lab. |  | Not Assigned |  | Unassigned | High | Waiting | 10 | 0 | C.D: 70%, K.L: 30%
C9 | Instant Messaging to Professors | As a student, I want an app to instantly message my professors during lectures, so I can clarify doubts without drawing attention. |  | Not Assigned |  | Unassigned | Low | Waiting | 4 | 0 | E.F: 40%, G.H: 30%, K.L: 30%
C10 | Convenient Messaging | As a student, I want an app with a class-wide forum, so I can seek help outside of help center hours and leverage peer insights. |  | Not Assigned |  | Unassigned | Low | Waiting | 5 | 0 | A.B: 40%, C.D: 30%, E.F: 30%
Social and Collaborative Stories
S1 | Connections with Similar Students | As a computer science student, I want to be able to easily find and connect with other students who are in the same course so that we can form study groups, share our learning resources, and support each other in the learning process. |  | Not Assigned |  | Unassigned | Medium | Waiting | 7 | 0 | A.B: 15%, C.D: 25%, E.F: 25%, G.H: 35%
S2 | A Platform to Make Friends/Connections within your Major | As a computer science student, I want a platform to interact with my peers, so that I can build connections and not feel alienated. |  | Not Assigned |  | Unassigned | Low | Waiting | 8 | 0 | C.D: 70%, K.L: 30%
S3 | Working Together with Peers | As a student, I want a platform to discuss assignments with my peers, so that I can gain diverse insights, especially when I can't attend office hours. |  | Not Assigned |  | Unassigned | Low | Waiting | 6 | 0 | A.B: 40%, C.D: 30%, E.F: 30%
Mentorship and Learning Stories
M1 | Receiving Help from Course Alumni | As a student who is navigating the challenging coursework, I want an application where I can reach out to students who have completed this class or people like alumni who have gone through similar challenges, so I can gain insights from their experiences, and feel more confined in my academic journey. |  | Not Assigned |  | Unassigned | High | Waiting | 8 | 0 | A.B: 40%, C.D: 60%
M2 | Choice Collaborations | As a computer science senior, I want to choose who I collaborate with, so that I can offer help based on my experiences without external pressures. |  | Not Assigned |  | Unassigned | Low | Waiting | 5 | 0 | A.B: 40%, C.D: 30%, E.F: 30%
Platform and User Experience Stories
P1 | Comparative Insights from Past Solutions | As a student, I want to use a platform tailored to academic needs, ensuring that it stands out from general-purpose platforms like Discord or Social Media, so I can more effectively engage and collaborate in my academic journey. |  | Not Assigned |  | Unassigned | Medium | Waiting | 7 | 0 | A.B: 40%, C.D: 60%
P2 | Around the Clock Help | As a student, I want a platform to anonymously seek immediate help, so I can get responses even outside typical hours and not fall behind on assignments. |  | Not Assigned |  | Unassigned | High | Waiting | 9 | 0 | C.D: 50%, K.L: 50%
P3 | Autocorrect Amenities | As a bilingual student, I want to have predictable and autocorrect features so that when I misspell or can’t remember something it will still make sense. |  | Not Assigned |  | Unassigned | Low | Waiting | 6 | 0 | G.H: 40%, I.J: 60%
Non-Technical Stories
NT1 | Feedback Mechanism Documentation | Before developing the feedback with emotional context feature, we need comprehensive documentation outlining the mechanism, potential emotional tags, and user guidelines for this feature. |  | Not Assigned |  | Unassigned | High | Waiting | 7 |  | A.B: 40%, C.D: 60%
NT2 | Feedback Tracking Workflow Mockups | Design a series of UI mockups detailing every step of the feedback tracking process, from submission to resolution, to ensure clarity and ease of use. |  | Not Assigned |  | Unassigned | High | Waiting | 8 |  | A.B: 20%, E.F: 30%, G.H: 25%, I.J: 25%
NT3 | Question Submission Guidelines | Prepare a set of guidelines for students to ensure they frame their questions in a constructive and respectful manner. |  | Not Assigned |  | Unassigned | Medium | Waiting | 4 |  | E.F: 50%, I.J: 50%
NT4 | Platform Differentiation Document | Prepare a document highlighting the unique features and benefits of our academic platform, distinguishing it from other general-purpose platforms like Discord. |  | Not Assigned |  | Unassigned | Medium | Waiting | 6 |  | C.D: 50%, K.L: 50%
NT5 | Feedback System Requirement Gathering | Conduct stakeholder interviews to collect detailed requirements for the feedback system. This would involve understanding desired features, any constraints, and expected outcomes. |  | Not Assigned |  | Unassigned | High | Waiting | 8 |  | A.B: 40%, C.D: 60%
NT6 | Feedback Form Mockups | Sketch mockups for the feedback submission form, considering elements like text boxes, emotion tags, attachment options, and any other desired features. |  | Not Assigned |  | Unassigned | High | Waiting | 7 |  | A.B: 20%, E.F: 30%, G.H: 25%, I.J: 25%
NT7 | Feedback Categorization Workshop | Organize a workshop with stakeholders to define categories for feedback. This would aid in organizing, prioritizing, and addressing feedback efficiently. |  | Not Assigned |  | Unassigned | Medium | Waiting | 6 |  | E.F: 50%, I.J: 50%
NT8 | Feedback Status Definitions | List out and define possible statuses for feedback, such as "submitted," "under review," "addressed," and "closed." |  | Not Assigned |  | Unassigned | Medium | Waiting | 5 |  | C.D: 50%, K.L: 50%
NT9 | Emotional Context Tagging Brainstorm | Hold brainstorming sessions to decide on emotional tags users can associate with their feedback, like "frustrated," "happy," or "confused. |  | Not Assigned |  | Unassigned | Medium | Waiting | 5 |  | A.B: 15%, C.D: 25%, E.F: 25%, G.H: 35%
NT10 | Feedback Resolution Template Creation | Design templates for feedback resolution, ensuring consistent responses and providing users with clarity on actions taken. |  | Not Assigned |  | Unassigned | Medium | Waiting | 5 |  | G.H: 40%, I.J: 60%
NT11 | Feedback Analytics Requirements | Meet with administrators or decision-makers to understand what analytics or reporting they would need from the feedback system, such as common pain points, frequency of certain feedback, etc. |  | Not Assigned |  | Unassigned | High | Waiting | 7 |  | A.B: 20%, E.F: 30%, G.H: 25%, I.J: 25%
NT12 | Feedback System User Testing Plan | Design a plan for usability testing of the feedback system. This would involve selecting participants, creating scenarios for them to test, and gathering feedback. |  | Not Assigned |  | Unassigned | High | Waiting | 8 |  | C.D: 70%, K.L: 30%
NT13 | Feedback System Accessibility Guidelines | Establish guidelines to ensure the feedback system is accessible to users with disabilities, ensuring inclusivity. |  | Not Assigned |  | Unassigned | Medium | Waiting | 6 |  | E.F: 40%, G.H: 30%, K.L: 30%
NT14 | Feedback System Feedback (Meta-feedback) | Design a mechanism for users to give feedback on the feedback system itself, helping in continuous improvement. |  | Not Assigned |  | Unassigned | Low | Waiting | 6 |  | A.B: 40%, C.D: 30%, E.F: 30%

## Deliverable 3 Sprint
Deliverable 3
ID | Story Title | User Story | Story Task Document | Sprint Number | Sprint Goal | Story Type | Story Priority | Story Status | Story Points | Story Points Completed | Names of Contributors | Contribution Percentage
Core User Stories
C1 | Feedback with Emotional Context | As a user of this system (student, professor, administrator, etc.) when I encounter a problem, I want to communicate not only the technical details but also how it makes me feel, so that the impact of the problem is fully understood. | C1 - Story Document | Not Assigned |  | Unassigned | Medium | Waiting | 8 | 0
C2 | Feedback History & Tracking | As a feedback provider, I want to track the status of my feedback, so I can understand where it's at in the review process and what actions are being taken. | C2 - Story Document | Not Assigned |  | Unassigned | Medium | Waiting | 8 | 0
C3 | Community Connection on Shared Issues | As a student, I want to connect with others who've shared similar feedback or faced similar issues, so we can collaborate on solutions or offer mutual support. | C3 - Story Document | Not Assigned |  | Unassigned | High | Waiting | 10 | 0
C4 | Direct Communication with Decision Makers | As a student, if I have a pressing issue, I want an option to message a specific authority, like a professor or department head, to directly address my concern. | C4 - Story Document | Not Assigned |  | Unassigned | Low | Waiting | 5 | 0
C5 | Anonymity | As a user (student, professor, administrator, etc.), I want to ask for help anonymously, so that I can alleviate my anxieties and ensure I succeed in the class. | C5 - Story Document | Not Assigned |  | Unassigned | High | Waiting | 8 | 0
C6 | Freedom to Ask Any Questions | As a student, I want to ensure that I can submit personal questions anonymously or questions that might not be “good” questions to get help without being judged by other classmates. |  | Not Assigned |  | Unassigned | High | Waiting | 8 | 0
C7 | Consistent Assistance | As a student, I want an active platform to consistently get assistance, so I can understand the material without repeatedly exposing my struggles. |  | Not Assigned |  | Unassigned | High | Waiting | 10 | 0
C8 | More Reliable than a Help Lab | As a student, I want an app to seek assistance, so that I can get help without the embarrassment I feel in a help lab. |  | Not Assigned |  | Unassigned | High | Waiting | 10 | 0
C9 | Instant Messaging to Professors | As a student, I want an app to instantly message my professors during lectures, so I can clarify doubts without drawing attention. |  | Not Assigned |  | Unassigned | Low | Waiting | 4 | 0
C10 | Convenient Messaging | As a student, I want an app with a class-wide forum, so I can seek help outside of help center hours and leverage peer insights. |  | Not Assigned |  | Unassigned | Low | Waiting | 5 | 0
Social and Collaborative Stories
S1 | Connections with Similar Students | As a computer science student, I want to be able to easily find and connect with other students who are in the same course so that we can form study groups, share our learning resources, and support each other in the learning process. |  | Not Assigned |  | Unassigned | Medium | Waiting | 7 | 0
S2 | A Platform to Make Friends/Connections within your Major | As a computer science student, I want a platform to interact with my peers, so that I can build connections and not feel alienated. |  | Not Assigned |  | Unassigned | Low | Waiting | 8 | 0
S3 | Working Together with Peers | As a student, I want a platform to discuss assignments with my peers, so that I can gain diverse insights, especially when I can't attend office hours. |  | Not Assigned |  | Unassigned | Low | Waiting | 6 | 0
Mentorship and Learning Stories
M1 | Receiving Help from Course Alumni | As a student who is navigating the challenging coursework, I want an application where I can reach out to students who have completed this class or people like alumni who have gone through similar challenges, so I can gain insights from their experiences, and feel more confined in my academic journey. |  | Not Assigned |  | Unassigned | High | Waiting | 8 | 0
M2 | Choice Collaborations | As a computer science senior, I want to choose who I collaborate with, so that I can offer help based on my experiences without external pressures. |  | Not Assigned |  | Unassigned | Low | Waiting | 5 | 0
Platform and User Experience Stories
P1 | Comparative Insights from Past Solutions | As a student, I want to use a platform tailored to academic needs, ensuring that it stands out from general-purpose platforms like Discord or Social Media, so I can more effectively engage and collaborate in my academic journey. |  | Not Assigned |  | Unassigned | Medium | Waiting | 7 | 0
P2 | Around the Clock Help | As a student, I want a platform to anonymously seek immediate help, so I can get responses even outside typical hours and not fall behind on assignments. |  | Not Assigned |  | Unassigned | High | Waiting | 9 | 0
P3 | Autocorrect Amenities | As a bilingual student, I want to have predictable and autocorrect features so that when I misspell or can’t remember something it will still make sense. |  | Not Assigned |  | Unassigned | Low | Waiting | 6 | 0
Non-Technical Stories
| Reviewing Past Feedback | As a project manager, I want to ensure that all feedback from Deliverable 2 is reviewed and tasks are created for any unaddressed comments, so that we can improve our project and meet the expectations set by our grading rubric. |  | Sprint 3 | The sprint goal is to refine our project based on past feedback, focusing on critical improvements that align with the grading rubric and ensure all team members are clear on enhancements. | Non-Functional (Technical) | High | In-progress | 5 | 10 | Entire Team | 100%
| Product Backlog Management | A a team member, I want to update our product backlog to include all columns and details from the project's documents and ensure it reflects the latest sprint numbers and story points, to avoid losing points due to missing or outdated information. |  | Sprint 3 | This sprint will concentrate on perfecting our product backlog, making sure it's fully updated and reflects all recent changes to maintain transparency and readiness for upcoming sprints. | Non-Functional (Technical) | High | In-progress | 8 | 10 | Andrew Bement | 100%
| Sprint Backlog Consistency | As a scrum master, I want to make sure that the Sprint Backlog 3 accurately reflects the product backlog and includes both technical and non-technical tasks such as documentation and UI mockups, to ensure a comprehensive approach to our sprint activities. |  | Sprint 3 | The sprint goal is to ensure the Sprint Backlog is a true mirror of the Product Backlog with added details for the upcoming sprint, incorporating all planned work including technical tasks and documentation. | Non-Functional (Technical) | Medium | In-progress | 3 | 10 | Andrew Bement | 100%
| Documenting Contribution | As a developer, I want to consistently commit to Github to show my contributions to the project, ensuring that all team members are recognized for their work and avoid a grade of zero. |  | Sprint 3 | The goal for this sprint is to maintain an accurate and timely record of contributions, promoting team accountability and visibility through consistent updates to our version control system. | Non-Functional (Technical) | High | In-progress | 2 | 10 | Entire Team | 100%
| Kanban Board Updates | As a project coordinator, I want to maintain an updated Kanban board with 20-40 meaningful tasks that show our progress and are properly assigned, ensuring clarity on project status and avoiding point deductions for under-assignment. |  | Sprint 3 | The sprint goal is to keep the Kanban board meticulously updated to reflect current project status and task ownership, ensuring that it provides a real-time snapshot of our collective progress. | Non-Functional (Technical) | Medium | In-progress | 5 | 10 | Entire Team | 100%
| Sprint Review Preparation | As a team, we want to follow the sprint review template and use it during our meetings, documenting our discussion to ensure that all aspects of the template are covered and that the most recent review is always at the top of our document. |  | Sprint 3 | This sprint is aimed at enhancing our review process, using the template to document our discussions thoroughly, making sure every point is addressed for a clear retrospection and future reference. | Non-Functional (Technical) | High | In-progress | 3 | 10 | Andrew Bement | 100%
| Addressing Architecture Design Comments | As a lead developer, I want to address all comments from Deliverable 2 on our architecture design, ensuring that we correct any issues and improve our design to meet the grading criteria. |  | Sprint 3 | The sprint goal is to refine our architecture based on feedback, with a commitment to addressing all comments and enhancing the design for compliance with grading standards. | Non-Functional (Technical) | Medium | In-progress | 6 | 10 | Sam Minor | 100%
| Completing SRS Requirements | As an analyst, I want to ensure that all sections of the SRS are filled out with the appropriate level of detail and that all feedback from Deliverable 2 is addressed, so we meet the minimum requirement numbers and avoid deductions. |  | Sprint 3 | Our sprint goal is to finalize the SRS document, ensuring it's comprehensive, addresses all feedback, and meets all the necessary requirements for quality and completeness. | Non-Functional (Technical) | Medium | In-progress | 7 | 10 | Samson Cournane | 100%
| Enhancing Use Case Artifacts | As a designer, I want to update our Use Case Models and Descriptions based on feedback and ensure that all our diagrams and descriptions match and follow the correct template, to achieve a high level of quality and avoid point losses. |  | Sprint 3 | The sprint goal is to polish our Use Case artifacts to a high standard, ensuring consistency and alignment with provided feedback for optimal quality and format compliance. | Non-Functional (Technical) | High | In-progress | 4 | 10 | Emily Brule | 100%
| Creating Sequence Diagrams | As a developer, I want to create comprehensive sequence diagrams for our application's main features and provide detailed descriptions for each step, ensuring accuracy and avoiding deductions for incomplete information. |  | Sprint 3 | This sprint will focus on developing detailed sequence diagrams that accurately describe our main features, committing to clarity and precision to enhance our technical documentation. | Non-Functional (Technical) | High | In-progress | 5 | 10 | Andrew Bement | 100%
| Progressing the Application Version | As a developer team, we want to show clear progress from Deliverable 2 by starting the implementation of at least one core feature and writing automated tests, ensuring we use test-driven development practices to gain additional points. |  | Sprint 3 | The sprint goal is to demonstrate tangible progress by implementing key features and establishing a robust automated testing framework, adhering to test-driven development methods. | Non-Functional (Technical) | High | In-progress | 4 | 10 | Kevin Menello | 100%
| Video Evidence of Functionality | As a team member, I want to participate in a recorded team meeting where we each demonstrate the application working on our machines, ensuring that we meet the requirements of the rubric and avoiding point deductions for non-compliance. |  | Sprint 3 | The goal this sprint is to collaboratively produce a video that showcases the application’s functionality, ensuring all team members are engaged and the product meets defined criteria. | Non-Functional (Technical) | Medium | In-progress | 5 | 10 | Entire Team | 100%